## Product Backlog
Product Name: | Mav’s Animal Shelter Software (MASS) | [6 empty] | Complete Fields in Green!!!
Team ID: | Pawsome Pals
| Team Member Name | [5 empty] | Initials | Student ID
Required | Ryan Laurents | [5 empty] | RJL | 1000763099
Sprint # | Remaining | Completed This Sprint |  |  |  | Comment
0 | 17 |  |  |  | Total | Total number of features (in column H)
1 | 14 | 3 |  |  | 1 | Total features left at the end of Sprint #1
2 | 11 | 3 |  |  | 2 | Total features left at the end of Sprint #2
3 | 8 | 3 |  |  | 3 | ...and so on
4 | 8 | 0
5 | 8 | 0
Note: Priority and specs for unfinished Features is subject to change at the end of each sprint at the whim of the Product Owner
Additional features may be proposed by the student but must be approved by the Product Owner in writing
Sprints
Feature ID | Priority | Required | Bonus | Est | Planned | Status | As a... | I want to... | So that I can… | Notes
EXIT | 1 | 1 |  | 5 | 1 | Finished in Sprint 1 | User | Exit the GUI program (File > Exit) | Use it again another day | Baseline an existing project’s code for class Mainwin, main function, and Makefile from e.g., MUSS (P6 – recommended), Nim (13), or Paint (17). Pare down GUI to what’s definitely reusable. Requires Mainwin::on_quit_click.
DOG | 2 | 1 |  | 21 | 1 | Finished in Sprint 1 | Staff | Create a new dog (Animal > New) | Track dogs seeking good homes | Requires Mainwin::on_create_animal; 1 dialog; classes Animal and Dog; Shelter::add_animal and attributes; and enum classes Gender and Dog_breed
LANIM | 3 | 1 |  | 5 | 1 | Finished in Sprint 1 | Staff | List animals (Animal > List Available) | See what animals are available | Requires Shelter::num_animals and animal; and Mainwin::on_animals_list; probably operator<< for dog
CAT | 4 | 2 |  | 8 | 2 | Finished in Sprint 2 | Staff | Create and list cats as well | Also put cats up for adoption | Requires class Cat; 1 Mainwin dialog to select Dog or Cat for Animal > New; and enum class Cat_breed; probably operator<< for Cat
RABBIT | 5 | 2 |  | 8 | 2 | Finished in Sprint 2 | Staff | Create and list rabbits as well | Also put rabbits up for adoption | Requires class Rabbit; and enum class Rabbit_breed; probably operator<< for Rabbit
CLIENT | 6 | 2 |  | 13 | 2 | Finished in Sprint 2 | Staff | Create a new client (Client > New) | Track candidate adopters | Requires Mainwin::on_create_client; 1 dialog; class Client; Shelter::add_client and attributes
LCLIENT | 7 | 3 |  | 5 | 3 | Finished in Sprint 3 | Client | List clients (Client > List) | See which clients are available | Requires Shelter::num_clients and client; and Mainwin::on_clients_list
ADOPT | 8 | 3 |  | 5 | 3 | Finished in Sprint 3 | Client | Adopt an animal (Client > Adopt Animal) | Adopt an animal! | Requires Client::adopted vector and Client::adopt method; 1 dialog
LADOPT | 9 | 3 |  | 8 | 3 | Finished in Sprint 3 | Staff | List adopted animals (Client > List Adopted and Animal > List Adopted) | See which client adopted which animal | Requires Client::num_adopted and animal methods; 1 dialog to select the client; Mainwin::on_list_adopted_click
SAVE | 10 | 4 |  | 13 |  |  | Manager | Save the data to a default file (File > Save) | Persist our data through the years | Requires Animal::save, Dog::save, Cat::save, and Rabbit::save; Shelter::save; Shelter::filename with getter and setter; and Mainwin::on_save_click
LOAD | 11 | 4 |  | 5 |  |  | Manager | Load the data from a default file (File > Open) | Persist our data through the years | Requires Animal::Animal(ist), Dog::Dog, Cat::Cat, and Rabbit::Rabbit; Shelter::Shelter; and Mainwin::on_open_click; dialog and logic for handling “dirty” data (baseline and adapt from Paint(17) if you don’t have it already)
NEW | 12 | 5 |  | 5 |  |  | Director | Create a new shelter (File > New) | Open additional shelters as needed | Requires Mainwin::on_new_shelter_click;
SAVEF | 13 | 5 |  | 5 |  |  | Director | Save the data to a specified file (File > Save As) | Backup or baseline a new shelter | Requires Mainwin::on_save_as_click; Shelter::set_filename; adding Gtk::FileChooserDialog (baseline from Paint(17) if you don’t have it already); set filename in Shelter
LOADF | 14 | 5 |  | 3 |  |  | Director | Load the data from a specified file (File > Open) | Work with multiple shelters | Requires adding Gtk::FileChooserDialog (baseline from Paint(17) if you don’t have it already)
ABOUT | 15 | 5 |  | 2 |  |  | Director | Display version and required attributions (Help > About) | Stay legal and in control | Requires adding Mainwin::on_about_click with Gtk::AboutDialog. Include a properly licensed logo!
PHOTO | 16 |  | TBD | 8 |  |  | Client | See photo and information about an available animal | Decide if it’s right for my family | Requires existing animal selection dialog + 1 dialog derived from Animal > New with a Gtk::Image, Mainwin::on_view_animal_click.
NANIM | 17 |  | TBD | 5 |  |  | Client | Create new animals and / or clients during adoption | Simplify the adoption process | Add “New Client” button to the client selection dialog; Add “New Animal” button to the animal selection dialog; add logic to integrate smoothly

## Sprint 01 Backlog
Sprint # | 1 |  | Complete Fields in Green!!!
Start on | 2019-10-29 |  | *** Create a new Sprint Backlog for EVERY SPRINT ***
End on | 2019-11-05
Demo on | TBD
| Remaining | Completed (this day)
Total Tasks | 12
Day 1 Left | 12 | 0
Day 2 Left | 12 | 0
Day 3 Left | 12 | 0
Day 4 Left | 12 | 0
Day 5 Left | 12 | 0
Day 6 Left | 12 | 0
Day 7 Left | 0 | 12
Task ID | Feature ID | Assigned To | Description | Status | Notes
1 | EXIT | Ryan Laurents | Create Mainwin.h/.cpp | Completed Day 7
2 | EXIT | Ryan Laurents | Create Window and basic GUI | Completed Day 7
3 | EXIT | Ryan Laurents | Add Menubar with File Menu | Completed Day 7
4 | EXIT | Ryan Laurents | Append Quit to File Menu | Completed Day 7
5 | EXIT | Ryan Laurents | Connect on_quit_click to close program when clicked | Completed Day 7
6 | DOG | Ryan Laurents | Create Animal, Dog, Shelter classes | Completed Day 7
7 | DOG | Ryan Laurents | Create enum classes gender and dog breed | Completed Day 7
8 | DOG | Ryan Laurents | Add on_new_animal_click to mainwin.h | Completed Day 7
9 | DOG | Ryan Laurents | Implement on_new_animal_click in mainwin.cpp | Completed Day 7
10 | LANIM | Ryan Laurents | Add List to Menu | Completed Day 7
11 | LANIM | Ryan Laurents | Connect on_list_animals_click to the menu item | Completed Day 7
12 | LANIM | Ryan Laurents | Add function call to the end of on_new_animal_click | Completed Day 7
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84

## Sprint 02 Backlog
Sprint # | 2 |  | Complete Fields in Green!!!
Start on | 2019-11-05 |  | *** Create a new Sprint Backlog for EVERY SPRINT ***
End on | 2019-11-12
Demo on | TBD
| Remaining | Completed (this day)
Total Tasks | 14
Day 1 Left | 14 | 0
Day 2 Left | 14 | 0
Day 3 Left | 14 | 0
Day 4 Left | 14 | 0
Day 5 Left | 14 | 0
Day 6 Left | 14 | 0
Day 7 Left | 0 | 14
Task ID | Feature ID | Assigned To | Description | Status | Notes
1 | CAT | Ryan Laurents | CREATE CLASS CAT | Completed Day 7
2 | CAT | Ryan Laurents | CREATE ENUM CLASS CAT BREED | Completed Day 7
3 | CAT | Ryan Laurents | CREATE MAP FOR CAT BREEDS | Completed Day 7
4 | CAT | Ryan Laurents | IMPLEMENT CAT CLASS | Completed Day 7
5 | RABBIT | Ryan Laurents | CREATE CLASS RABBIT | Completed Day 7
6 | RABBIT | Ryan Laurents | CREAT ENUM CLASS RABBIT BREED | Completed Day 7
7 | RABBIT | Ryan Laurents | CREATE MAP FOR RABBIT BREEDS | Completed Day 7
8 | RABBIT | Ryan Laurents | IMPLEMENT RABBIT CLASS | Completed Day 7
9 | CLIENT | Ryan Laurents | CREATE CLIENT CLASS | Completed Day 7
10 | CLIENT | Ryan Laurents | ADD CLIENT MENU | Completed Day 7
11 | CLIENT | Ryan Laurents | ADD "ADD CLIENT" SUBMENU | Completed Day 7
12 | CLIENT | Ryan Laurents | CONNECT ON NEW CLIENT CLICK | Completed Day 7
13 | CLIENT | Ryan Laurents | ADD ERROR HANDLING FOR CLIENT INFO | Completed Day 7
14 | EXIT | Ryan Laurents | ADD ICONS FOR TOOLBAR | Completed Day 7
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84

## Sprint 03 Backlog
Sprint # | 3 |  | Complete Fields in Green!!!
Start on | 2019-11-12 |  | *** Create a new Sprint Backlog for EVERY SPRINT ***
End on | 2019-11-19
Demo on | TBD
| Remaining | Completed (this day)
Total Tasks | 16
Day 1 Left | 16 | 0
Day 2 Left | 16 | 0
Day 3 Left | 0 | 16
Day 4 Left | 0 | 0
Day 5 Left | 0 | 0
Day 6 Left | 0 | 0
Day 7 Left | 0 | 0
Task ID | Feature ID | Assigned To | Description | Status | Notes
1 | LCLIENT | Ryan Laurents | ADD LIST CLIENTS TO CLIENTS MENU | Completed Day 3
2 | LCLIENT | Ryan Laurents | ADD TITLES FOR ADOPTIONS AND CLIENTS | Completed Day 3
3 | LCLIENT | Ryan Laurents | ADD NEW AREA FOR CLIENTS TO BE LISTED | Completed Day 3
4 | LCLIENT | Ryan Laurents | ADD ON LIST CLIENTS METHOD | Completed Day 3
5 | LCLIENT | Ryan Laurents | IMPLEMENT LIST CLIENTS | Completed Day 3
6 | ADOPT | Ryan Laurents | ADD ADOPT ANIMAL TO CLIENTS MENU | Completed Day 3
7 | ADOPT | Ryan Laurents | ADD ON ADOPT CLICK AND ATTACH TO ADOPT MENU | Completed Day 3
8 | ADOPT | Ryan Laurents | ADD ADOPTED VECTOR IN CLIENT | Completed Day 3
9 | ADOPT | Ryan Laurents | ADD REMOVE ANIMAL FUNCTION IN SHELTER | Completed Day 3
10 | ADOPT | Ryan Laurents | IMPLEMENT ADOPT ANIMAL | Completed Day 3
11 | LADOPT | Ryan Laurents | ADD NUM_ADOPTED TO CLIENT | Completed Day 3
12 | LADOPT | Ryan Laurents | ADD FUNCTION TO RETURN ADOPTED[INDEX] | Completed Day 3
13 | LADOPT | Ryan Laurents | ADD LIST ADOPTED IN ANIMAL/CLIENT MENUS | Completed Day 3
14 | LADOPT | Ryan Laurents | ADD LABELS ON MAIN AREA FOR ADOPTED LIST | Completed Day 3
15 | LADOPT | Ryan Laurents | IMPLEMENT LIST ADOPTED | Completed Day 3
16 | LADOPT | Ryan Laurents | ADD REFRESH BUTTON BECAUSE ARTHRITIS | Completed Day 3
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84

## Sprint 04 Backlog
Sprint # | 4 |  | Complete Fields in Green!!!
Start on | 2019-11-19 |  | *** Create a new Sprint Backlog for EVERY SPRINT ***
End on | 2019-11-26
Demo on | TBD
| Remaining | Completed (this day)
Total Tasks | 1
Day 1 Left | 1 | 0
Day 2 Left | 1 | 0
Day 3 Left | 1 | 0
Day 4 Left | 1 | 0
Day 5 Left | 1 | 0
Day 6 Left | 1 | 0
Day 7 Left | 1 | 0
Task ID | Feature ID | Assigned To | Description | Status | Notes
1 |  |  | --> Add tasks to complete each feature for this sprint
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84

## Sprint 05 Backlog
Sprint # | 5 |  | Complete Fields in Green!!!
Start on | 2019-11-26 |  | *** Create a new Sprint Backlog for EVERY SPRINT ***
End on | 2019-12-03
Demo on | TBD
| Remaining | Completed (this day)
Total Tasks | 1
Day 1 Left | 1 | 0
Day 2 Left | 1 | 0
Day 3 Left | 1 | 0
Day 4 Left | 1 | 0
Day 5 Left | 1 | 0
Day 6 Left | 1 | 0
Day 7 Left | 1 | 0
Task ID | Feature ID | Assigned To | Description | Status | Notes
1 |  |  | --> Add tasks to complete each feature for this sprint
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84