## Product Backlog
Product Name: | C1325 Mav’s Ultimate Sweet Shop (MUSS) | [5 empty] | Complete Fields in Green!!!
Team ID:
Name: | Ryan Laurents
Initials: | RJL
Student ID: | 1000763099
Teaming is not available for this assignment!
Optional teaming may be available in future assignments
| Remaining | Completed (this sprint)
Total Features | 23 |  | Total
Sprint 1 Left | 18 | 5 | 1
Sprint 2 Left | 18 | 0 | 2 |  | Note: You are NOT penalized for not reaching 0 features remaining! Some of these are bonus features.
Note: Priority of unfinished Features is subject to change at the end of each sprint at the whim of the Product Owner
Additional features or alternate priorities may be proposed by the student but must be approved by the Product Owner in writing
Sprints
Feature ID | Priority |  | Planned | Status | As a... | I want to... | So that... | Notes
SPRINT 1 / Homework 5 starts here – due OCTOBER 15
Mainwin | 1 |  | 1 | Finished in Sprint 1 | Sales Clerk | Add a main window with text data area | can use the application with a mouse | The text data area is a Gtk::Label on which you can later display lists of sweets or orders
FileQuit | 2 |  | 1 | Finished in Sprint 1 | Sales Clerk | Add a menu bar with File > Quit | can exit from the window
FileNew | 3 |  | 1 | Finished in Sprint 1 | Sales Clerk | Add File > New Store | can instance a new store without exiting
SweetsAdd | 4 |  | 1 | Finished in Sprint 1 | Sales Clerk | Add Sweets > Add | can create new products from dialogs | For this feature you may use 2 dialogs, for name and price
SweetsList | 5 |  | 1 | In Work | Sales Clerk | Add Sweets > List | can see a menu of our products and their prices | Put the output in the text data area (i.e., the Gtk::Label below the menu)
HelpAbout | 6 |  | 1 | Finished in Sprint 1 | Sales Clerk | Add a Help > About menu | know who created the program and its resources
Sensitivity1 | 7 |  | 1 |  | Sales Clerk | Manage menu sensitivity | avoid making errors | Sweets > List should be greyed out if no Sweets have been defined yet
FileNewBtn | 8 |  | 1 |  | Sales Clerk | Add a tool bar with a New Store button | operate MUSS with buttons | This does exactly the same thing as File > New; the stock icon is fine
FileQuitBtn | 8 |  | 1 |  | Sales Clerk | Add an Exit button aligned to the right | operate MUSS with buttons | This does exactly the same thing as File > Quit; the stock icon is fine
SweetsAddBtn | 8 |  | 1 |  | Sales Clerk | Add a New Sweet button | operate MUSS with buttons | This does exactly the same thing as Sweet > Add; credit your icon in Help > About
SweetsListBtn | 8 |  | 1 |  | Sales Clerk | Add a List Sweets button | operate MUSS with buttons | This does exactly the same thing as Sweet > List; credit your icon in Help > About
| 9 |  |  |  | Sales Clerk | Add rich text (Pango) to the about dialog | The about text is easier to understand
SweetsAddDlg | 10 |  | 1 |  | Sales Clerk | Use a single dialog for Sweets > Add | deal with fewer dialogs | The dialog should have Name and Price fields, and Create and Cancel buttons
StatusBar | 10 |  | 1 |  | Sales Clerk | Add a status bar below the text data area | obtain better feedback on program operation | This is just a window-wide Gtk::Label with messages “Added [sweetname]”, “New sweet canceled”, “Order [n] placed”, “Order canceled”, “New shop created”
SPRINT 2 / Homework 6 starts here – due OCTOBER 22
OrdersPlace | 11 |  | 2 | In Work | Sales Clerk | Add Orders > Place | create orders with the mouse | You may use a sequence of dialogs, each selecting quantity and sweet, to build up the order
OrdersList | 12 |  | 2 |  | Sales Clerk | Add Orders > List | view existing orders | Ask the user for an order number, then display the order in the text data area
Sensitivity2 | 13 |  | 2 |  | Sales Clerk | Manage menu sensitivity | avoid making errors | Orders > Place should be greyed out if no sweets have been defined, and Orders > List if no orders have been defined (remember to handle File > New Store!)
OrdersPlaceBtn | 14 |  | 2 |  | Sales Clerk | Add a Place an Order button | operate MUSS with buttons | This does exactly the same thing as Orders > Place; credit your icon in Help > About
OrdersListBtn | 14 |  | 2 |  | Sales Clerk | Add a List Orders button | operate MUSS with buttons | This does exactly the same thing as Orders > List; credit your icon in Help > About
Pango | 15 |  | 2 |  | Sales Clerk | Replace custom About with a Gtk::About Dialog | The about text is even easier to understand
OrdersPlaceDlg | 16 |  | 2 |  | Sales Clerk | Use a single dialog for Orders > Place | deal with fewer dialogs | The dialog must show sweets and quantities already added, allow selection of sweet from a drop-down and quantity via text or drop-down, with Add, Finish, and Cancel buttons
Save | 17 |  | 2 |  | Sales Clerk | File > Save the data to a .muss file | maintain data when the program exits | You may use a single predefined filename or the FileChooserDialog, and may define any file format you like
Load | 17 |  | 2 |  | Sales Clerk | File > Load data from a .muss file | maintain data when the program exits | Consider how to handle existing unsaved data when File > Open is requested

## Sprint 01 Backlog
Sprint # | 1 |  | Complete Fields in Green!!!
Start on | 2019-10-03 |  | *** Create a new Sprint Backlog for EVERY SPRINT ***
End on | 2019-10-15
Demo on | TBD
| Remaining | Completed (this day)
Total Tasks | 26
Day 1 Left | 26 | 0
Day 2 Left | 26 | 0
Day 3 Left | 26 | 0
Day 4 Left | 18 | 8
Day 5 Left | 18 | 0
Day 6 Left | 16 | 2
Day 7 Left | 16 | 0
| Feature ID |  | Description | Status | Notes
| Mainwin |  | Add code to main-gui.cpp to create and run window instance | Completed Day 4 | See e.g., the nim in-class example to help with these
| Mainwin |  | Add a private Gtk::Label to mainwin.h and Mainwin constructor for the text data area | Completed Day 4
| FileQuit |  | In Mainwin constructor, add VBox and MenuBar with File>Quit | Completed Day 4
| FileQuit |  | Add and implement protected on_quit_click() method | Completed Day 4 | The close() method is usually best
| FileNew |  | Add and implement protected on_new_store_click() method and File>New | Completed Day 4
| SweetsAdd |  | Add a Sweets menu and an Add item | Completed Day 4
| SweetsAdd |  | Implement utility to read line of text via a simple dialog | Completed Day 4 | OR create a custom dialog to read name and price in one step
| SweetsAdd |  | Add and implement protected on_add_sweet_click() method | Completed Day 4 | Get the name and price to instance a Sweet to pass to _store
| SweetsList |  | Add and implement protected on_list_sweets_click() method and Sweets>List | In Work
| HelpAbout |  | Add a Help menu and an About item | Completed Day 6
| HelpAbout |  | Add and implement protected on_help_click() to create a MessageDialog with app and your name, license, and credits | Completed Day 6 | Or skip right to the Gtk::AboutDialog class
| Sensitivity1 |  | At end of constructor, set_sensitivity false for list sweets menu item
| Sensitivity1 |  | At end of successful SweetsAdd, set_sensitivity true “ “ “
| FileNewBtn |  | In constructor, add a Gtk::Toolbar just under the MenuBar
| FileNewBtn |  | Configure Stock::NEW button connected to on_new_store_click()
| FileQuitBtn |  | Configure Stock::QUIT button connected to on_quit_click()
| SweetsAddBtn |  | Select appropriate Sweets icons scaled to 32x32 to 64x64ish size
| SweetsAddBtn |  | Configure custom button connected to on_add_sweet_click()
| SweetsListBtn |  | Configure custom button connected to on_list_sweets_click()
| SweetsAddDlg |  | Create a Gtk::Dialog
| SweetsAddDlg |  | Add an HBox containing a Gtk::Label and a Gtk::Entry for name
| SweetsAddDlg |  | Add an HBox containing a Gtk::Label and a Gtk::Entry for price
| SweetsAddDlg |  | Add buttons, show, and exit if Cancel was clicked
| SweetsAddDlg |  | Convert price text to a double, instance a Sweet, and add to _store
| StatusBar |  | Add a Gtk::label with HExpand just after the text data area
| StatusBar |  | Add set_text() method calls on the status bar where messages are needed

## Sprint 02 Backlog
Sprint # | 2 |  | Complete Fields in Green!!!
Start on | 2019-10-15 |  | *** Create a new Sprint Backlog for EVERY SPRINT ***
End on | 2019-10-22
Demo on | TBD
| Remaining | Completed (this day)
Total Tasks | 5
Day 1 Left | 5 | 0
Day 2 Left | 5 | 0
Day 3 Left | 5 | 0
Day 4 Left | 5 | 0
Day 5 Left | 5 | 0
Day 6 Left | 5 | 0
Day 7 Left | 2 | 3
| Feature ID |  | Description | Status | Notes
| OrdersPlace |  | Add "Orders" Menu | Completed Day 7 | Create your own task (“to do”) list to the left
| OrdersPlace |  | Add "Place" submenu in Orders menu | Completed Day 7
| OrdersPlace |  | Use dialogs to ask which sweet and quantity they want | In Work
| OrdersList |  | Add "List" submenu to Orders Menu | Completed Day 7
| OrdersList |  | Track items and show on main window